## Hoja1
Requirements & Planning |  | Design |  | Implementation |  | Testing |  | Deployment
Task | Time (hr) | Task | Time (hr) | Task | Time (hr) | Task | Time (hr) | Task | Time (hr)
List all requirements | 0.5 | Design main screen | 1 | Develop main screen | 2 | Test all screens | 1 | Deployment | 0.5
Research animations in Angular routing | 0.5 | Design genoma view | 1 | Develop genoma screen | 2
Research animations for Angular components | 0.5 | Design job view | 1 | Develop job screen | 2
Define screens | 1